## Overdue Action Reminder
Action ID | Action Title | Owner | Owner Email | Department | Priority | Status | Start Date | Due Date | Days Overdue
ACT-1001 | Resolve ATM downtime complaints - Ikeja cluster | Ese Ile | ese.ile@sterling.ng | Digital Banking | Low | Overdue | 2026-08-05 | 2026-08-22 | 50
ACT-1002 | Fix failed transfer reversal delays | Ukuchukwu Odozi | ukuchukwu.odozi@sterling.ng | Credit & Loans | High | In Progress | 2026-07-19 | 2026-08-12 | 60
ACT-1003 | Update USSD error messaging | Ukuchukwu Odozi | samuel.omobuwa@sterling.ng | Digital Banking | High | Overdue | 2026-08-09 | 2026-08-21 | 51
ACT-1004 | Close card dispute backlog | Samuel Omobuwa | samuel.omobuwa@sterling.ng | Card Services | Low | Open | 2026-07-19 | 2026-09-02 | 39
ACT-1005 | Investigate mobile app login failures | Samuel Omobuwa | samuel.omobuwa@sterling.ng | Payments & Transfers | Medium | In Progress | 2026-08-22 | 2026-08-17 | 55
ACT-1006 | Reconcile duplicate debit alerts | Samuel Omobuwa | samuel.omobuwa@sterling.ng | Contact Centre | High | Open | 2026-08-09 | 2026-08-28 | 44
ACT-1007 | Root cause: POS decline spike | Samuel Omobuwa | samuel.omobuwa@sterling.ng | Branch Operations | High | Pending Review | 2026-07-31 | 2026-08-29 | 43
ACT-1008 | Follow up on branch queue complaints | Samuel Omobuwa | samuel.omobuwa@sterling.ng | IT Service Desk | High | Open | 2026-07-24 | 2026-09-10 | 31
ACT-1009 | Escalate unresolved chargeback cases | Ese Ile | ese.ile@sterling.ng | Digital Banking | Low | Pending Review | 2026-08-04 | 2026-08-30 | 42
ACT-1010 | Address delayed loan disbursement complaints | Ukuchukwu Odozi | ukuchukwu.odozi@sterling.ng | Credit & Loans | High | Closed | 2026-08-20 | 2026-08-21
ACT-1011 | Fix email notification delivery gaps | Samuel Omobuwa | samuel.omobuwa@sterling.ng | IT Service Desk | High | In Progress | 2026-08-16 | 2026-08-31 | 41
ACT-1012 | Review call centre wait time breaches | Samuel Omobuwa | samuel.omobuwa@sterling.ng | Credit & Loans | Medium | In Progress | 2026-08-12 | 2026-08-30 | 42
ACT-1013 | Resolve BVN linkage failures | Samuel Omobuwa | samuel.omobuwa@sterling.ng | Credit & Loans | Medium | Overdue | 2026-08-18 | 2026-08-17 | 55
ACT-1014 | Address recurring OTP delivery failures | Amina Gellal | samuel.omobuwa@sterling.ng | Branch Operations | Medium | Open | 2026-08-05 | 2026-09-11 | 30
ACT-1015 | Close out social media escalations - billing | Charles Ifem | Charles.ifem@sterling.ng | IT Service Desk | High | Closed | 2026-08-08 | 2026-08-09
ACT-1016 | Investigate diaspora transfer delays | Charles Ifem | Charles.ifem@sterling.ng | Contact Centre | High | Due Today | 2026-08-09 | 2026-08-27 | 45
ACT-1017 | Fix statement generation errors | Charles Ifem | Charles.ifem@sterling.ng | Credit & Loans | Medium | Open | 2026-07-28 | 2026-09-05 | 36
ACT-1018 | Address token generation failures | Samuel Omobuwa | samuel.omobuwa@sterling.ng | Card Services | High | In Progress | 2026-07-18 | 2026-09-10 | 31
ACT-1019 | Resolve airtime purchase failures | Eno Bassey | eno.bassy@sterling.ng | Branch Operations | Low | Open | 2026-07-28 | 2026-08-30 | 42
ACT-1020 | Review complaint reopens - card issues | Eno Bassey | eno.bassy@sterling.ng | Payments & Transfers | Medium | Overdue | 2026-08-17 | 2026-08-10 | 62
ACT-1001 | Resolve ATM downtime complaints - Ikeja cluster | Ese Ile | ese.ile@sterling.ng | Digital Banking | Low | Overdue | 2026-08-05 | 2026-08-22 | 50
ACT-1002 | Fix failed transfer reversal delays | Ukuchukwu Odozi | ukuchukwu.odozi@sterling.ng | Credit & Loans | High | In Progress | 2026-07-19 | 2026-08-12 | 60
ACT-1003 | Update USSD error messaging | Ukuchukwu Odozi | samuel.omobuwa@sterling.ng | Digital Banking | High | Overdue | 2026-08-09 | 2026-08-21 | 51
ACT-1004 | Close card dispute backlog | Samuel Omobuwa | samuel.omobuwa@sterling.ng | Card Services | Low | Open | 2026-07-19 | 2026-09-02 | 39
ACT-1005 | Investigate mobile app login failures | Samuel Omobuwa | samuel.omobuwa@sterling.ng | Payments & Transfers | Medium | In Progress | 2026-08-22 | 2026-08-17 | 55
ACT-1006 | Reconcile duplicate debit alerts | Samuel Omobuwa | samuel.omobuwa@sterling.ng | Contact Centre | High | Open | 2026-08-09 | 2026-08-28 | 44
ACT-1007 | Root cause: POS decline spike | Samuel Omobuwa | samuel.omobuwa@sterling.ng | Branch Operations | High | Pending Review | 2026-07-31 | 2026-08-29 | 43
ACT-1008 | Follow up on branch queue complaints | Samuel Omobuwa | samuel.omobuwa@sterling.ng | IT Service Desk | High | Open | 2026-07-24 | 2026-09-10 | 31
ACT-1009 | Escalate unresolved chargeback cases | Ese Ile | ese.ile@sterling.ng | Digital Banking | Low | Pending Review | 2026-08-04 | 2026-08-30 | 42
ACT-1010 | Address delayed loan disbursement complaints | Ukuchukwu Odozi | ukuchukwu.odozi@sterling.ng | Credit & Loans | High | Closed | 2026-08-20 | 2026-08-21
ACT-1011 | Fix email notification delivery gaps | Samuel Omobuwa | samuel.omobuwa@sterling.ng | IT Service Desk | High | In Progress | 2026-08-16 | 2026-08-31 | 41
ACT-1012 | Review call centre wait time breaches | Samuel Omobuwa | samuel.omobuwa@sterling.ng | Credit & Loans | Medium | In Progress | 2026-08-12 | 2026-08-30 | 42
ACT-1013 | Resolve BVN linkage failures | Samuel Omobuwa | samuel.omobuwa@sterling.ng | Credit & Loans | Medium | Overdue | 2026-08-18 | 2026-08-17 | 55
ACT-1014 | Address recurring OTP delivery failures | Amina Gellal | samuel.omobuwa@sterling.ng | Branch Operations | Medium | Open | 2026-08-05 | 2026-09-11 | 30
ACT-1015 | Close out social media escalations - billing | Charles Ifem | Charles.ifem@sterling.ng | IT Service Desk | High | Closed | 2026-08-08 | 2026-08-09
ACT-1016 | Investigate diaspora transfer delays | Charles Ifem | Charles.ifem@sterling.ng | Contact Centre | High | Due Today | 2026-08-09 | 2026-08-27 | 45
ACT-1017 | Fix statement generation errors | Charles Ifem | Charles.ifem@sterling.ng | Credit & Loans | Medium | Open | 2026-07-28 | 2026-09-05 | 36
ACT-1018 | Address token generation failures | Samuel Omobuwa | samuel.omobuwa@sterling.ng | Card Services | High | In Progress | 2026-07-18 | 2026-09-10 | 31
ACT-1019 | Resolve airtime purchase failures | Eno Bassey | eno.bassy@sterling.ng | Branch Operations | Low | Open | 2026-07-28 | 2026-08-30 | 42
ACT-1020 | Review complaint reopens - card issues | Eno Bassey | eno.bassy@sterling.ng | Payments & Transfers | Medium | Overdue | 2026-08-17 | 2026-08-10 | 62
Formulas:
Days Overdue = IF([Status]="Closed","",IF(TODAY()>[Due Date],TODAY()-[Due Date],0))